## Executive Summary
MILA26 Workspace Tab Audit - Editable Review Workbook
Status | Sprint 15 audit-first review complete
Purpose | Tab-by-tab audit before broadening functionality: actions, status, information, artefacts, persistence ownership, and cross-tab data flow.
Core rule | Tabs are visual structure only. Engineering Bot, Advisor mode, lifecycle state, Product Vault, Evidence Vault, and Contract Ops must share one lifecycle picture.
Strongest current matches | Investor Wallets, Subscription, Redemption, Contract Ops, Evidence Vault, and persistent AI panel.
Main gaps | Product Setup, Asset Servicing, and Maturity need dedicated panels. Expert mode, stale labels, Contract Ops density, and legacy SCP remnants need cleanup.
Recommended next sprint | Sprint 16 workspace completion pass, not a new feature expansion.
Decision Summary
Priority | Item Count | Recommendation | Reason
P0 | 5 | Implement first | Missing core tab panels and active-control cleanup.
P1 | 3 | Implement after P0 | Clarity and evidence-readiness improvements.
P2 | 3 | Later polish | Useful, but not blocking prototype usability.
How To Use This Workbook
1. Review the Findings and Gaps sheet first.
2. Use Tab Review to mark Agree / Amend / Defer for each tab.
3. Use Sprint 16 Backlog to confirm implementation priorities.
4. Use Feedback Decisions to record product direction before coding Sprint 16.

## Findings and Gaps
Findings and Gaps
ID | Type | Area | Finding / Gap | User Impact | Recommendation | Priority | User Decision | Notes
F-01 | Fit | AI panel | Engineering/Advisor panel persists across tabs and keeps cross-stage context. | Matches the intended modern AI interaction model. | Keep this as the center of the workspace. | Keep
F-02 | Fit | Investor Wallets | Up to 50 wallets, duplicate detection, generated wallet pack, explicit private-key export, whitelist and allocation handoff. | Supports realistic demo and token distribution workflow. | Keep mostly intact; polish copy/warnings only. | Keep
F-03 | Fit | Subscription | Captures permitted stablecoins, subscription window, minimum amount, payment address, and payment per token. | Supports subscription-redemption template configuration. | Keep and later add presets if they remain customisable. | Keep
F-04 | Fit | Redemption | Captures redemption window, delay, redemption wallet, payout stablecoin, and payout per token. | Supports delayed redemption design at parameter level. | Keep parameter focus until execution adapter is designed. | Keep
F-05 | Fit | Contract Ops | Supports wallet-signed deployment, Record NAV, Wallet Whitelist, and Allocation/Mint. | Shows real blockchain capability, not only mockups. | Preserve adapters and gates; improve grouping. | Keep
F-06 | Fit | Evidence Vault | Durable save/load exists for provider-derived evidence and generated artefacts after snapshot. | Supports investor/auditor evidence story. | Add readiness hints and tab-origin grouping later. | Keep
G-01 | Gap | Product Setup | Tab exists but lacks a dedicated setup panel. | User may not know what to review, fill in, or approve in this stage. | Add brief status, assumptions, open questions, and artefact actions. | P0
G-02 | Gap | Asset Servicing | Tab exists but has no dedicated servicing panel. | User cannot work from the tab for NAV/update/servicing workflows. | Add Record NAV handoff, servicing log, and draft future notice placeholders. | P0
G-03 | Gap | Maturity | Tab exists but has no dedicated maturity parameter panel. | User cannot capture maturity date, closeout method, or closeout readiness. | Add parameter-only Maturity panel before live closeout execution. | P0
G-04 | Gap | Top bar | Guided/Expert controls look active, but Expert is not yet meaningful. | Creates a false capability signal. | Wire Expert properly or visibly disable it until real. | P0
G-05 | Gap | Naming | Some stale Investor Registry and SCP language remains. | Can confuse users and future coding work. | Rename user-facing remnants to Investor Wallets and remove/quarantine legacy SCP markup. | P0/P2
G-06 | Gap | Contract Ops UX | Functionally strong but dense. | User may struggle to find the right operation sequence. | Group into Deployment, Investor Ops, Asset Ops, Allocation/Mint. | P1
G-07 | Gap | Overview | Overview could better show current objective, blockers, and saved state. | User may miss what to do next after switching tabs. | Add compact next-work panel only if it avoids clutter. | P1
G-08 | Gap | Evidence Vault | It is not always obvious what can be saved now and what prerequisite is missing. | User may think evidence is durable before saving. | Add save-readiness hints and tab-origin grouping. | P1

## Tab Review
Tab-by-Tab Review
Tab | Current State | User Actions | Status / Information | Artefacts / Persistence | Fit | Gap | Sprint 16 Decision | User Decision | Notes
Overview | AI-first entry surface with lifecycle context and passive right rail. | Ask Engineering/Advisor, follow next actions, save/load via visible workspace controls. | Lifecycle snapshot, Product Vault, open items, recent activity. | Conversation is local-session; generated artefacts can be saved where supported. | Good primary entry point. | Needs clearer current objective / next blockers / saved state overview. | Add compact next-work panel only if it reduces clutter.
Product Setup | Visual tab exists, but no dedicated setup panel. | Requirement Brief, Engineering Brief, Smart Contract Spec generation via shared AI/artifact actions. | Product facts, assumptions, open questions partly exist in AI responses and artefacts. | Generated artifact records persist after explicit save. | Correct lifecycle stage exists. | User may not know what to review or fill in when landing on the tab. | Add dedicated Product Setup panel with brief statuses, assumptions, open questions, and artefact actions.
Investor Wallets | Dedicated working panel. | Add wallets, generate test wallet pack, prepare explicit test-only export, hand off wallet to whitelist/allocation. | Registered, ready, whitelisted, remaining capacity, validation. | Workspace snapshot persists wallet rows; private keys are not persisted. | Strong match. | Minor copy polish and export warning can improve confidence. | Keep mostly intact; add only small clarity improvements if needed.
Subscription | Dedicated working parameter panel. | Capture stablecoins, subscription window, minimum amount, payment address, payment per token. | Parameter readiness and validation. | Workspace snapshot persists lifecycle parameters. | Strong match for template readiness. | Free-text stablecoin input is flexible but less guided. | Add presets later if they do not constrain custom products.
Contract Ops | Dedicated working operation panel. | Deploy, Record NAV, Whitelist Wallet, Allocation/Mint. | Wallet/deployment/readiness/evidence status. | Provider-derived evidence can be saved through Evidence Vault; local wallet session remains local. | Strong technical functionality. | Dense layout; duplicated actions can make priority unclear. | Reorganise visually into Deployment, Investor Ops, Asset Ops, Allocation/Mint while reusing current state.
Asset Servicing | Visual tab exists, but no dedicated servicing panel yet. | Record NAV exists in Contract Ops. Future notices/updates are not yet implemented. | Current NAV operation status is visible elsewhere. | Record NAV evidence can be saved when provider-derived. | Underlying first operation exists. | User cannot yet work from the Asset Servicing tab; investor update workflow is not represented. | Add dedicated Asset Servicing panel with Record NAV handoff, servicing log, and future investor notice placeholders.
Redemption | Dedicated working parameter panel. | Capture redemption window/date, delay, redemption wallet, payout stablecoin, payout per token. | Parameter readiness and validation. | Workspace snapshot persists lifecycle parameters. | Strong match for template readiness. | No live redemption request or delayed payout operation yet. | Keep parameter focus; later add execution adapter/evidence contract.
Maturity | Visual tab exists, but no dedicated maturity panel yet. | No clear maturity input surface. | Maturity status exists in lifecycle/read models. | Workspace snapshot can carry maturity fields once captured. | Correct stage exists. | User cannot capture maturity date, closeout method, or closeout readiness. | Add parameter-only Maturity panel before live closeout execution.
Evidence Vault | Dedicated working evidence/artifact persistence panel. | Save/load evidence records and generated artefacts. | Current/stale/historical labels, record lists. | SQLite-backed local MVP persistence. | Strong match. | Needs clearer what-can-be-saved-now guidance from each tab. | Add save-readiness hints and tab-origin grouping later.

## Sprint 16 Backlog
Sprint 16 Backlog
Priority | Backlog Item | Why It Matters | Suggested Scope | Acceptance Test / Evidence | Owner | User Decision | Notes
P0 | Product Setup tab panel | A lifecycle tab should not feel empty when the user is setting up the product. | Show Requirement Brief, Engineering Brief, assumptions, open questions, and artefact actions from shared state. | React test for panel content and actions; E2E navigation confirms visible setup content.
P0 | Asset Servicing tab panel | Asset servicing is core to MILA26 value proposition, not an optional side feature. | Show NAV recording status, Contract Ops handoff, servicing log, and draft future investor notice placeholders. | React test for panel and Record NAV handoff; E2E navigation confirms servicing surface.
P0 | Maturity parameter panel | The user explicitly needs maturity closeout planning. | Capture maturity date, closeout method, and closeout readiness as parameters only. | React test for field updates and lifecycle snapshot; no live closeout claim.
P0 | Guided/Expert cleanup | Active-looking but unwired controls reduce trust. | Wire meaningful mode state or visibly disable Expert until implemented. | Test verifies no false active control state.
P0 | Investor Wallets naming cleanup | Old Investor Registry wording creates drift. | Rename user-facing remnants where appropriate. | Text search and tests updated.
P1 | Contract Ops re-layout | The tab is powerful but dense. | Group into Deployment, Investor Ops, Asset Ops, Allocation/Mint. | React/E2E tests verify operations remain wired.
P1 | Overview next-work panel | Helps users understand current objective and blockers. | Add only if it avoids clutter. | Screenshot review confirms center panel remains clean.
P1 | Evidence Vault readiness hints | Prevents user confusion about durable vs local-session records. | Show what can be saved and missing prerequisites. | Tests verify readiness copy for snapshot/evidence/artifact states.
P2 | Stablecoin presets | Can reduce input friction. | Add presets while preserving custom values. | Tests confirm custom stablecoins remain possible.
P2 | Legacy SCP cleanup | Hidden legacy markup can drift from current UI. | Remove or quarantine once Contract Ops coverage is complete. | Text search confirms no user-facing legacy remnants.
P2 | Browser screenshot review | Protects UX quality after panel work. | Capture desktop and mobile screenshots for newly functional tabs. | Screenshots show no overlap/clutter.

## Feedback Decisions
User Feedback Decisions
Decision ID | Question | Recommended Default | Decision | Reason / Notes
D-01 | Are Product Setup, Asset Servicing, and Maturity the right P0 tab priorities? | Yes. They are the biggest tab-level gaps and complete the visual lifecycle.
D-02 | Should Asset Servicing include investor notices now? | Add draft-only placeholders now; implement live sending later.
D-03 | Should Maturity remain parameter-only for now? | Yes. Capture planning inputs before live closeout execution.
D-04 | Should Contract Ops be redesigned in Sprint 16? | Only light re-layout. Preserve adapters and shared state.
D-05 | Should Expert mode be wired now? | Disable visibly unless we define a real Expert workflow.

## Acceptance Criteria
Acceptance Criteria
ID | Criterion | Applies To | Verification | Pass / Fail | Notes
AC-01 | Every lifecycle tab has a dedicated working panel or a clear handoff. | All tabs | React tests and E2E navigation.
AC-02 | No active-looking button remains unwired. | Top bar and all panels | React tests and manual review.
AC-03 | New panels read/write shared lifecycle state, not tab-local lifecycle stores. | Product Setup, Asset Servicing, Maturity | Code review of state ownership.
AC-04 | Existing Investor Wallets, Subscription, Redemption, Contract Ops, and Evidence Vault tests pass. | Regression suite | npm test target suites.
AC-05 | New panels have React tests and at least one E2E flow. | Sprint 16 work | Test run and browser screenshot review.
AC-06 | Durable state and evidence labels remain honest. | Persistence and Evidence Vault | Evidence/persistence tests and UI copy review.

## Sources
Source Review
Source | Purpose
docs/product/workspace-tab-audit.md | Source audit document
src/App.tsx | Workspace UI and tab panels
src/domain/workspacePresentation.ts | Visual tab/status/product vault presentation model
src/domain/lifecycleState.ts | Shared lifecycle state/read model
tests/app-chat-panel.test.tsx | React regression coverage
tests/e2e/mila26.spec.ts | Browser/E2E coverage
docs/operations/live-sepolia-readiness.md | Live Sepolia/evidence planning context